## Sheet1
Issues Tracking Table
Issue ID | Category | Description of Issue | Severity | Root Cause | Resolution / Fix Applied | Status
ISSUE-01 | XAML / Layout | XLS0415 error: FallbackTarget property not found on Image control. | High | <Image.FallbackTarget> child element is invalid syntax in .NET MAUI. | Replaced FallbackTarget tag with native inline Source="{Binding FlagUrl, FallbackValue='?'}". | RESOLVED
ISSUE-02 | Git / Terminal | fatal: not a git repository error when running git commands in PowerShell. | Medium | Git repository was not initialized in project root directory prior to committing. | Executed git init, staged project files, created initial commit, and linked remote origin. | RESOLVED
ISSUE-03 | Git / Permissions | Permission denied error on .vs cache index file during git add .. | High | Visual Studio process locked hidden cache index files inside .vs folder. | Created .gitignore file to exclude .vs/, bin/, obj/, and .user files from tracking. | RESOLVED
ISSUE-04 | REST API | App displayed "Failed to process country information" error on startup. | High | Full REST Countries endpoint payload triggered desktop HttpClient timeout and strict deserialization exceptions. | Scoped query fields, added user-agent header, used dynamic JsonNode parsing, and implemented fallback dataset. | RESOLVED
ISSUE-05 | UI Layout | Region and Sort By pickers overlapped each other in dark mode layout. | Medium | Grid column definitions in CountriesPage.xaml shared overlapping label space. | Wrapped each picker inside dedicated VerticalStackLayout containers within separate Grid columns. | RESOLVED
ISSUE-06
ISSUE-07
ISSUE-08
ISSUE-09